## Sheet1
Vendor ID | Risk Description | Treatment | Action Item | Owner | Due Date | Status | Evidence | Residual Risk
VEN-003 | Lack of mandatory hardware MFA for contractor support accounts accessing ticketing platform | Mitigate | Enforce FIDO2/WebAuthn step-up authentication across all contractor access portals | Identity & Access Management Team | 2026-09-30 | In Progress | IAM Configuration Policy v3.2 & Admin Screenshot | Low
VEN-003 | Extended remediation SLA of 60 days for CVSS High vulnerabilities in customer support integration | Mitigate | Execute formal security addendum binding vendor to 30-day patch SLA | Information Security / Legal | 2026-09-15 | In Progress | Draft Contract Addendum v1.4 | Low
VEN-003 | Administrative audit log retention limited to 90 days in customer support tool | Mitigate | Configure centralized SIEM export and extend log retention to 365 days | IT Infrastructure Operations | 2026-10-15 | Open | SIEM Retention Policy Settings & Integration Log | Low
VEN-011 | Session recording logs stored without dedicated encryption key segregation | Mitigate | Migrate session recordings to enterprise KMS-managed encrypted bucket with automated key rotation | IT Helpdesk Lead | 2026-09-20 | Completed | AWS KMS Key Policy JSON & Bucket Configuration | Low
VEN-014 | Sub-processor notification timeline set to 14 days in standard terms for travel booking platform | Accept with Control | Establish weekly automated vendor registry check for sub-processor updates | Finance & Travel Operations | 2026-08-30 | Completed | Automated Scraping Script Logs & Registry Snapshot | Medium