## Sheet1
Test ID | Scenario | Date | Participants | Expected result | Actual result | Pass/Fail | Finding | Corrective action | Owner | Retest date
BCP-TST-001 | AWS Multi-Region Failover Simulation for Payment Gateway API | 2026-03-15 | DevOps Lead, Payments Engineering Team, FinOps Manager | Automated DNS failover to secondary region (us-west-2) within 120 seconds with zero transaction drop. | Failover completed successfully in 95 seconds; all transaction queues successfully processed without data loss. | Pass | Slight latency spike observed during initial region switchover due to DNS propagation delay. | Tune DNS TTL values on AWS Route 53 health checks from 60 seconds down to 30 seconds. | DevOps Engineering Lead | 2026-06-15
BCP-TST-002 | Customer Support Ticketing Platform Cloud Outage Tabletop | 2026-04-10 | Support Triage Leads, Security Incident Response Team, Director of Customer Success | Emergency agent dispatch and emergency mobile notification routing activated within 15 minutes. | Notification workflows triggered within 8 minutes; however, two secondary responders experienced stale credentials. | Pass with Findings | Secondary on-call personnel lacked updated SSO token sync for emergency mobile access. | Implement monthly automated SSO token refresh verification for all designated incident responders. | Identity & Access Management Team | 2026-05-10
BCP-TST-003 | Immutable Backup Restoration & Ransomware Recovery Drill | 2026-05-20 | Infrastructure Reliability Lead, Database Administrator, Security Engineer | Complete core database restoration from WORM-locked S3 daily backup within 2 hours (RTO < 2h). | Database fully restored and verified for integrity in 1 hour 45 minutes from immutable storage snapshot. | Pass | Restoration script manual verification steps caused a 15-minute delay prior to automated validation. | Automate the integrity verification script directly into the restoration pipeline runner. | Infrastructure Reliability Lead | 2026-08-20
BCP-TST-004 | Payroll & HR Remote Workforce Continuity Simulation | 2026-06-05 | Payroll Manager, HR Operations Specialist, IT Helpdesk Lead | Successful fallback to secure cloud backup ledger and remote VDI access for payroll processing. | Virtual desktop gateway experienced authentication timeouts due to concurrent user spike. | Fail | VDI resource pool auto-scaling limits were configured too low for full departmental concurrency. | Increase cloud VDI instance auto-scaling ceiling and pre-warm instances during disaster drills. | IT Enterprise Systems Lead | 2026-07-05
BCP-TST-005 | Crisis Management Team (CMT) Strategic Communications Walkthrough | 2026-07-12 | Chief Executive Officer, General Counsel, Head of Communications, Chief Compliance Officer | Drafting and authorizing external stakeholder communication and regulatory breach notice within 1 hour. | Draft communication approved and distributed via secure channels in 45 minutes; all legal review gates cleared. | Pass | Contact directory template contained two outdated phone numbers for secondary legal counsel. | Update enterprise contact directory management workflow to quarterly automated verification. | General Counsel | 2026-10-12