## Audit Plan
INTERNAL AUDIT MASTER PLAN & TEST SCHEDULE
Detailed listing of internal audit tests, compliance requirements, evidence, and execution status.
Audit ID | Audit Area | Control / Requirement | Owner | Evidence Required | Test Method | Planned Date | Status | Notes / Comments
AUD-001 | Access Control | SOC2 CC6.1 - User Access Review performed quarterly | J. Smith | Quarterly review sign-off sheets & ticketing logs | Sample 25 privileged users and verify documented management approval | 2026-03-15 | Closed | Completed with zero exceptions noted.
AUD-002 | Access Control | ISO 27001 A.9.2.6 - Removal of access rights upon termination | J. Smith | HR termination notices and Active Directory disable timestamps | Cross-reference HR termination report with AD deactivation logs for 15 samples | 2026-03-30 | Fieldwork Complete | Pending final confirmation on 2 contractor accounts.
AUD-003 | Change Management | SOC2 CC8.1 - Changes tested and approved prior to production deployment | M. Davis | Change tickets, QA test sign-offs, and deployment logs | Sample 20 production changes and inspect approval workflows | 2026-04-10 | In Progress | Testing in progress; 3 tickets missing QA sign-off.
AUD-004 | Change Management | ISO 27001 A.12.1.2 - Emergency change documentation and retroactive approval | M. Davis | Emergency change tickets and Post-Incident Review docs | Inspect all emergency changes for Q1 and verify retroactive approval within 48h | 2026-04-20 | Not Started | Scheduled for next sprint.
AUD-005 | Data Privacy & GDPR | GDPR Art. 32 - Encryption of personal data at rest and in transit | A. Johnson | Cloud configuration exports and SSL/TLS cipher suite reports | Review AWS KMS key policies and SSL Labs scan results for public endpoints | 2026-05-05 | Not Started | Scheduled.
AUD-006 | Data Privacy & GDPR | GDPR Art. 17 - Data subject erasure ('Right to be Forgotten') mechanism | A. Johnson | Data deletion logs and automated script execution reports | Walkthrough data deletion workflow and inspect sample deletion logs | 2026-05-18 | Not Started | Scheduled.
AUD-007 | Incident Management | SOC2 CC7.3 - Security incidents detected, logged, and investigated timely | R. Taylor | SIEM alert logs, incident response tickets, and post-mortem reports | Sample 10 security alerts and verify response time against SLA | 2026-06-01 | Not Started | Scheduled.
AUD-008 | Vendor Risk Management | ISO 27001 A.15.1.1 - Third-party security risk assessment prior to onboarding | S. Lee | Completed vendor questionnaires, SOC2 reports, and risk scoring sheets | Sample 8 critical third-party vendors and review due diligence files | 2026-06-15 | Not Started | Scheduled.
AUD-009 | Backup & Recovery | SOC2 CC9.1 - Regular backups of critical data and periodic restoration testing | K. Patel | Backup job execution reports and annual restoration test results | Inspect Q1 backup logs and observe annual database restoration test | 2026-07-01 | Not Started | Scheduled.
AUD-010 | Physical Security | ISO 27001 A.11.1.6 - Visitor access controls and escort logging | P. Gomez | Visitor sign-in logs and CCTV retention policies | Sample 5 days of visitor logs and reconcile with physical badge swipes | 2026-07-20 | Not Started | Scheduled.
AUD-011 | Network Security | ISO 27001 A.13.1.1 - Firewall rule review and unnecessary port restriction | N. Vance | Firewall rulebase configuration and bi-annual review sign-offs | Review firewall change logs and verify bi-annual rule review was performed | 2026-08-05 | Not Started | Scheduled.
AUD-012 | Asset Management | ISO 27001 A.8.1.1 - Inventory of hardware and software assets maintained | E. Wright | MDM inventory export and software asset management (SAM) database | Reconcile MDM active device list with HR active employee roster | 2026-08-22 | Not Started | Scheduled.
AUD-013 | HR Security | ISO 27001 A.7.1.1 - Background screening for employees handling sensitive data | H. Green | Background check confirmation letters from screening provider | Sample 12 newly hired employees and verify background check completion certificate | 2026-09-10 | Not Started | Scheduled.
AUD-014 | HR Security | ISO 27001 A.7.2.2 - Information security awareness training for all staff | H. Green | LMS completion reports and annual training tracking records | Inspect Q2 company-wide security training completion report for compliance rate | 2026-09-25 | Not Started | Scheduled.
AUD-015 | Access Control | SOC2 CC6.3 - Password complexity and Multi-Factor Authentication (MFA) enforced | J. Smith | IdP (Okta/Azure AD) security policy settings and user configuration export | Verify IdP policy enforces 12+ char complexity, lockout, and mandatory MFA | 2026-10-10 | Not Started | Scheduled.

## Dashboard
INTERNAL AUDIT DASHBOARD — FY2026
Audit Plan Summary & Metrics
Status | Test Count | % of Total
Not Started | 0 | #DIV/0!
In Progress | 0 | #DIV/0!
Fieldwork Complete | 0 | #DIV/0!
Draft Report | 0 | #DIV/0!
Closed | 0 | #DIV/0!
Total Audits | 0 | #DIV/0!

## Reference Data
Status Options | Audit Areas
Not Started | Access Control
In Progress | Change Management
Fieldwork Complete | Data Privacy & GDPR
Draft Report | Incident Management
Closed | Vendor Risk Management
Backup & Recovery
Physical Security
Network Security
Asset Management
HR Security