## Committee Meetings
Security Governance Committee Meeting Register
Fictional / Educational Simulation Dataset ¦ Committee Year: 2026
Meeting ID | Date | Attendees | Main Risks | Compliance Issues | Incidents | Decisions Required | Decision Made | Action Owner | Due Date | Status
CM-2026-01 | 2026-01-15 | CISO, CIO, Head of Legal, Head of Risk, IT Infrastructure Lead | Credential stuffing spikes, legacy VPN vulnerability exposure | GDPR annual audit preparation gaps in legacy HR systems | Severity 3 ransomware attempt on staging file server (contained) | Approve emergency migration from legacy VPN to cloud-native ZTNA solution | Approved $120,000 budget reallocation for ZTNA implementation | IT Infrastructure Lead | 2026-02-15 | Completed
CM-2026-02 | 2026-02-18 | CISO, Chief Compliance Officer, Head of Human Resources, Procurement Director | Third-party vendor data leakage risks, unmonitored SaaS sprawl | ISO 27001 surveillance audit finding on vendor risk management documentation | None | Mandate automated security risk assessments for all new vendor onboarding requests | Approved mandatory vendor risk assessment workflow in procurement portal | Vendor Risk Manager | 2026-03-31 | In Progress
CM-2026-03 | 2026-03-18 | CISO, Chief Privacy Officer, Marketing Director, Customer Support Head | Data subject consent tracking failures in mobile application SDKs | CCPA / GDPR regulatory inquiry regarding targeted tracking cookies | Severity 2 accidental exposure of test user PII in public repository | Authorize immediate suspension of non-compliant marketing analytics SDKs | Approved SDK suspension and mandatory privacy code review | Chief Privacy Officer | 2026-04-10 | Completed
CM-2026-04 | 2026-04-15 | CISO, Head of Enterprise Risk, Application Development Lead, QA Lead | Unpatched open-source software libraries, insecure API endpoints | PCI-DSS compliance gap regarding annual external penetration testing findings | Severity 3 API rate-limiting bypass attempt | Approve integration of automated software composition analysis (SCA) in CI/CD pipeline | Approved mandatory SCA gating for all production code deployments | Application Development Lead | 2026-05-15 | Completed
CM-2026-05 | 2026-05-20 | CISO, Physical Security Lead, Facilities Director, HR Operations Manager | Tailgating in server rooms, unauthorized visitor access to corporate offices | SOC 2 physical security control deficiency in badge reader logs | Tailgating incident detected at regional data center secondary entrance | Approve capital expenditure for biometric turnstiles at primary and secondary facilities | Approved biometrics upgrade project with phased rollout | Physical Security Lead | 2026-07-31 | In Progress
CM-2026-06 | 2026-06-17 | CISO, Cloud Security Architect, DevOps Lead, Finance Director | Cloud configuration drift, overly permissive IAM roles across AWS/Azure accounts | SOC 2 cloud infrastructure logging deficiencies | Severity 3 misconfigured S3 bucket containing non-sensitive operational logs | Mandate automated Cloud Security Posture Management (CSPM) auto-remediation policies | Approved strict auto-remediation policy for publicly exposed cloud resources | Cloud Security Architect | 2026-07-15 | Completed
CM-2026-07 | 2026-07-15 | CISO, Business Continuity Manager, Operations Director, Legal Counsel | Supply chain disruption, ransomware resilience of backup infrastructure | ISO 22301 business continuity testing frequency non-compliance | None | Approve quarterly cross-functional disaster recovery simulation exercises | Approved mandatory quarterly tabletop and technical failover drills | Business Continuity Manager | 2026-08-31 | In Progress
CM-2026-08 | 2026-08-19 | CISO, Head of Internal Audit, Compliance Manager, Risk Committee Chair | Delayed remediation of high-risk audit findings past agreed deadlines | Internal audit finding backlog exceeding threshold limits | None | Enforce executive escalation policy and freeze non-essential budget for delinquent owners | Approved executive escalation protocol for audit findings overdue by > 60 days | Internal Audit Director | 2026-09-30 | In Progress
CM-2026-09 | 2026-09-16 | CISO, Head of Training & Awareness, HR Director, Communications Lead | Phishing simulation failure rates exceeding acceptable departmental limits | Mandatory annual security awareness training completion lagging in sales division | Severity 3 successful credential harvesting test among executive assistants | Approve mandatory remedial micro-training and simulated phishing consequences policy | Approved mandatory remedial training and manager escalation for repeat failures | Training & Awareness Manager | 2026-10-31 | Open
CM-2026-10 | 2026-10-21 | CISO, Chief Legal Counsel, Threat Intelligence Lead, Incident Response Commander | Advanced persistent threat (APT) campaigns targeting financial sector supply chains | Regulatory reporting readiness under new cyber incident notification mandates | Severity 2 sophisticated spear-phishing campaign targeting finance executives | Authorize retainer agreement for external incident response and forensic legal counsel | Approved retainer expansion with top-tier cybersecurity incident response firm | Incident Response Commander | 2026-11-30 | Open