## Remediation and Retest Register
Enterprise GRC Remediation & Retest Tracking Register
Tracking control deficiencies, corrective action plans, retest verification, and formal closure decisions
Finding ID | Remediation | Owner | Due Date | Status | Evidence Submitted | Retest Procedure | Retest Result | Closure Decision
FIND-001 | All privileged service accounts added to quarterly review scope and IAM automated recertification workflow. | IAM Lead | 2026-08-15 | Closed | Updated IAM workflow config & Q3 privilege attestation sheet | Compare privileged account population against latest quarterly review roster. | Pass | Closed
FIND-002 | Deploy automated MDM enrollment agents to all remote contractor endpoints to enforce disk encryption. | Endpoint Security Lead | 2026-08-20 | Closed | Intune MDM compliance policy export and encryption status report | Verify BitLocker/FileVault encryption status across 100% of contractor endpoints. | Pass | Closed
FIND-003 | Update incident response escalation runbook to mandate 15-minute SLA paging for Sev-1 alerts. | SOC Manager | 2026-08-25 | Closed | Approved POL-004 v3.1 update and PagerDuty routing rule export | Inspect PagerDuty escalation policy routing rules and test simulated Sev-1 alert page. | Pass | Closed
FIND-004 | Implement automated token expiration and 90-day secret rotation for non-human service accounts. | DevOps Lead | 2026-09-15 | In Progress | Pending vault policy integration | Audit Azure Key Vault secret rotation schedules and token age logs. | Pending | Open
FIND-005 | Conduct targeted phishing refresher training for high-risk departmental groups. | HR Training Lead | 2026-09-30 | In Progress | Pending LMS completion reports | Verify completion records against departmental roster and analyze follow-up simulation click rates. | Pending | Open