## Remediation Plan
GULFPAY — VENDOR RISK TREATMENT / REMEDIATION PLAN
Actions arising from the inherent risk assessment, security questionnaire, and evidence review. Track to closure and re-evaluate residual risk.
Vendor: | GulfPay FZ-LLC | Service: | Payment processing & wallet services | Assessment Date: | 2026-08-15 | Plan Owner: | Vendor Risk Team
Inherent Risk Rating: | High | Target Residual Risk: | Medium or below | Next Review: | 2026-11-15 | Status Summary: | In Progress
Finding | Action | Owner | Priority | Target Date | Evidence Required | Status | Residual Risk
F-01: Multi-factor authentication is not enforced for all privileged and remote administrative accounts supporting the payment platform. | Enforce MFA (preferably phishing-resistant) on all privileged, administrative, and remote access paths to systems that process or store payment and customer data. Provide configuration evidence and policy extract. | GulfPay – CISO / IAM Lead | Critical | 2026-09-30 | MFA policy + configuration screenshots / export for admin & remote access; exception list (if any) with compensating controls | Open | High
F-02: No current SOC 2 Type II (or equivalent independent assurance report) covering Security and Availability for the payment services in scope. | Commission or provide a current SOC 2 Type II (or ISO 27001 certificate + Statement of Applicability + recent internal audit summary) covering the services used. Share report under NDA. | GulfPay – Compliance Lead | High | 2026-12-15 | SOC 2 Type II report (or ISO 27001 cert + SoA) with period end within last 12 months; bridge letter if needed | In Progress | Medium
F-03: Annual independent penetration test results for the customer-facing and API payment channels were not provided or are older than 12 months. | Engage an independent third party to perform penetration testing of internet-facing applications and APIs in scope. Remediate Critical/High findings and supply executive summary + remediation status. | GulfPay – Security Engineering | High | 2026-10-31 | Pen test executive summary, scope, date, and confirmation that Critical/High items are closed or have agreed compensating controls | Open | Medium
F-04: Privileged access reviews are performed ad-hoc; no formal recertification evidence for the last 12 months. | Implement formal privileged access recertification at least quarterly. Provide latest completed review pack (list of accounts, reviewers, decisions, and closure of excess access). | GulfPay – IAM Lead | High | 2026-10-15 | Completed privileged access review evidence (dated within last 90 days) including sign-off | Open | Medium
F-05: Sub-processor list is incomplete and change-notification process is not contractually defined for GulfPay’s downstream providers. | Publish a complete, current sub-processor list (name, location, purpose) and formalize advance notification of material changes (minimum 30 days) in the DPA / contract schedule. | GulfPay – Privacy / Legal | High | 2026-09-30 | Current sub-processor schedule + contractual clause (or amendment) for notification of changes | In Progress | Medium
F-06: Encryption in transit for some internal service-to-service payment data flows uses TLS 1.1 or is not explicitly mandated to TLS 1.2+. | Enforce TLS 1.2 or higher (prefer TLS 1.3) for all external and internal payment-related data in transit. Disable weak protocols/ciphers. Provide standards document and sample configuration evidence. | GulfPay – Security Architecture | High | 2026-10-31 | Encryption standard / policy extract + configuration evidence confirming TLS 1.2+ only | Open | Low
F-07: Disaster recovery (DR) test for the primary payment processing environment has not been evidenced within the last 12 months. | Conduct a DR test (tabletop or technical failover) against defined RTO/RPO for critical payment services. Document results, gaps, and remediation actions. | GulfPay – Infrastructure / BCP Lead | Medium | 2026-11-30 | DR test report including date, scope, RTO/RPO achieved, and open actions | Open | Medium
F-08: Incident response plan does not explicitly define customer notification timelines aligned to contractual and regulatory requirements (e.g., 72 hours for personal data breaches). | Update IRP to include clear customer and regulator notification triggers and timelines. Align with contract and applicable privacy/payment regulations. Provide revised plan excerpt. | GulfPay – Incident Response Lead | Medium | 2026-10-15 | Updated IRP section on external notification (customers / regulators) with timelines | In Progress | Low
F-09: Vulnerability management SLAs for Critical findings are not documented; sample evidence shows remediation beyond 30 days in two cases. | Document and implement patch/vulnerability SLAs (e.g., Critical ≤ 15–30 days). Provide policy extract and latest Critical/High ageing report demonstrating adherence. | GulfPay – Vulnerability Management | Medium | 2026-10-31 | Vulnerability / patch management policy with SLAs + recent ageing report for Critical/High items | Open | Low
F-10: No formal evidence of secure data deletion / media sanitization procedures for customer payment data at end of retention or contract termination. | Document secure deletion and media sanitization procedures (aligned to NIST or equivalent). Confirm ability to issue certificate of destruction on request at offboarding. | GulfPay – Data Governance / Security | Medium | 2026-11-15 | Data deletion / media sanitization procedure + sample certificate of destruction template | Open | Low
F-11: Security awareness training completion for staff with access to payment systems is not evidenced for the current annual cycle. | Complete mandatory security awareness (and role-based) training for all relevant staff. Provide completion metrics and confirmation for personnel supporting the services in scope. | GulfPay – HR / Security Awareness | Medium | 2026-09-30 | Training completion report (rate and date) for staff in scope of payment services | In Progress | Low
F-12: Joiner-mover-leaver (JML) process lacks evidence of timely access revocation on termination (sample showed >24h in one case). | Tighten JML controls so that access to payment systems is revoked on or before last working day (or within defined same-day SLA). Provide process description and recent termination samples. | GulfPay – IAM / HR Ops | Medium | 2026-10-31 | JML procedure extract + anonymised sample of recent leaver access revocation timestamps | Open | Low
F-13: Backup restore testing frequency is annual only; no evidence of more frequent restores for critical payment databases. | Increase restore testing for critical payment data stores to at least quarterly. Document successful restore tests and retention of backup media in a separate location/region. | GulfPay – Infrastructure | Low | 2026-11-30 | Backup policy + latest restore test evidence for critical payment systems | Open | Low
F-14: Contractual right to audit / security assessment is not clearly reflected in the current service agreement with GulfPay. | Negotiate inclusion (or confirmation) of a reasonable audit / assessment clause and cooperation obligation for security questionnaires and evidence requests. | Internal – Legal / Vendor Management (with GulfPay Legal) | Low | 2026-12-31 | Executed contract amendment or side letter confirming audit / assessment rights | Open | Acceptable
Priority / Status / Residual Risk Legend
Priority | Critical | High | Medium | Low
Status | Open | In Progress | Closed | Deferred
Residual Risk | Critical | High | Medium | Low | Acceptable

## Summary
GULFPAY REMEDIATION PLAN — SUMMARY
By Priority
Priority | Count
Critical | 1
High | 5
Medium | 6
Low | 2
By Status
Status | Count
Open | 10
In Progress | 4
Closed | 0
Deferred | 0
Total Findings | 14
Notes
• Residual Risk is the expected risk level after the action is completed and evidence accepted.
• Close a finding only when required evidence has been received and reviewed.
• Re-score inherent/residual risk for GulfPay after Critical and High items are closed.
• Escalate any Critical action that misses its Target Date to the Vendor Risk governance forum.

## Instructions
GULFPAY REMEDIATION PLAN — GUIDANCE
Purpose
Track treatment actions for findings identified during the GulfPay vendor risk assessment (questionnaire, evidence review, and inherent risk scoring). Drive residual risk down to an acceptable level.
Column definitions
Finding | Concise statement of the gap or control weakness (reference ID F-xx).
Action | Specific, measurable remediation required of GulfPay (or internal teams where noted).
Owner | Accountable party — usually a GulfPay role; internal owners noted where the action is contractual/legal.
Priority | Critical / High / Medium / Low — based on likelihood and impact to payment services and data.
Target Date | Agreed date for completion and evidence delivery.
Evidence Required | Artifacts needed to demonstrate the action is complete and effective.
Status | Open ¦ In Progress ¦ Closed ¦ Deferred.
Residual Risk | Expected risk rating after successful closure (Critical / High / Medium / Low / Acceptable).
Workflow
1. Agree actions and target dates with GulfPay; record in this plan.
2. GulfPay delivers evidence against each action.
3. Reviewer validates evidence; update Status to Closed and confirm Residual Risk.
4. On closure of Critical/High items, update the overall vendor residual risk rating and monitoring plan.
5. Report overdue Critical/High items to the vendor risk governance forum.