## Corrective Action Plan
CORRECTIVE ACTION PLAN (CAP) & ISSUE TRACKING
Comprehensive remediation tracker for audit findings, corrective actions, priorities, retest schedules, and closure status.
Finding ID | Corrective Action | Owner | Priority | Target Date | Status | Evidence Required | Retest Date | Retest Result | Closure
FND-001 | Revoke inactive vendor accounts and enforce automated 90-day deactivation policy in Active Directory | J. Smith | High | 2026-03-31 | Closed | AD account status export & deactivation logs | 2026-04-05 | Pass | Verified Closed
FND-002 | Update change management policy to mandate peer review and QA sign-off prior to production deployment | M. Davis | High | 2026-04-15 | Closed | Updated policy document & Jira workflow configuration | 2026-04-20 | Pass | Verified Closed
FND-003 | Implement automated daily encryption verification checks for all AWS S3 buckets containing sensitive data | A. Johnson | Medium | 2026-05-10 | In Progress | AWS Config compliance dashboard screenshot | 2026-05-15 | Pending | Open
FND-004 | Conduct emergency patch deployment for identified high-severity vulnerabilities on legacy internal servers | N. Vance | Critical | 2026-04-30 | Closed | Tenable post-patch vulnerability scan report | 2026-05-02 | Pass | Verified Closed
FND-005 | Perform comprehensive annual disaster recovery tabletop simulation with all executive department heads | K. Patel | Medium | 2026-06-15 | In Progress | DR exercise minutes, attendance sheet, and after-action report | 2026-06-20 | Pending | Open
FND-006 | Obtain and archive missing SOC2 Type II compliance reports for 3 third-party SaaS vendors | S. Lee | Medium | 2026-05-20 | Closed | Vendor compliance folder exports | 2026-05-22 | Pass | Verified Closed
FND-007 | Revise privacy policy and establish documented data subject access request (DSR) response workflow | A. Johnson | High | 2026-05-30 | In Progress | Published privacy policy update and ticketing workflow template | 2026-06-05 | Pending | Open
FND-008 | Enforce mandatory multi-factor authentication (MFA) across all administrative and service accounts | J. Smith | Critical | 2026-04-01 | Closed | IdP security settings configuration export | 2026-04-03 | Pass | Verified Closed
FND-009 | Update physical visitor log standard operating procedures to include mandatory badge escorts | P. Gomez | Low | 2026-06-01 | Closed | Updated physical security SOP document & security guard sign-off | 2026-06-05 | Pass | Verified Closed
FND-010 | Complete quarterly user access re-certification for financial systems and review privilege exceptions | J. Smith | High | 2026-04-10 | Closed | Signed quarterly access review sign-off sheet | 2026-04-12 | Pass | Verified Closed
FND-011 | Implement centralized log retention policy in SIEM ensuring minimum 365-day retention for audit trails | R. Taylor | High | 2026-06-30 | Pending Verification | SIEM storage policy configuration export | 2026-07-05 | Pending | Pending Sign-off
FND-012 | Conduct mandatory security awareness refresher training for all personnel with overdue status | H. Green | Medium | 2026-05-15 | Closed | LMS 100% completion tracking report | 2026-05-18 | Pass | Verified Closed

## Dashboard
CORRECTIVE ACTION PLAN DASHBOARD
CAP Status Summary & Metrics
Action Status | Count | % of Total
Open | 0 | 0%
In Progress | 3 | 25%
Pending Verification | 1 | 8.333%
Closed | 8 | 66.67%
Total Corrective Actions | 12 | 100%

## Reference Data
Priority Options | Status Options | Retest Result Options | Closure Options
Critical | Open | Pass | Verified Closed
High | In Progress | Fail | Pending Sign-off
Medium | Pending Verification | Pending | Open
Low | Closed | N/A | Deferred